## Pre-Evaluation Questionnaire
Contractor Performance Pre-Evaluation Questionnaire
Please complete this set of questions prior to starting your evaluation to ensure the evaluation template is customized to suit your particular project and / or the stage you are at in your project.
If no, exclude
1 | Is this the Final Evaluation or an Interim Evaluation? | Final | 34-40 | Exclude these for interim evaluations
2 | Have there been any Change Orders? | Yes | 25
3 | Have any submittals, other than the baseline schedule, been required from the Contractor yet? | Yes | 6
4 | Have there been any deficiencies? | Yes | 15
5 | Has testing, including equipment commissioning commenced and/or been completed? | Yes | 16
6 | Were there any incidents/accidents involving the General Public? | Yes | 23
7 | Has the Contractor received any written notices? | Yes | 28
8 | Have there been any service delivery issues (i.e. complaints, inquiries, claims)? | Yes | 32
9 | Was there a Contractually or Region approved start date the Contractor was to meet? | Yes | 1
10 | Were there any Safety Issues? | Yes | 22
11 | Were any stop work orders issued by the Region, MOL, TSSA, other Agencies? | Yes | 24
12 | Were permits including environmental requirements (i.e. Conservation Authority, MOE, OBC) required as part of this project? | Yes | 8
13 | Does project close-out require Operations and Maintenance Manuals and/or record documents and drawings to be submitted by the Contractor? | Yes | 39
After completing these questions please move on to the Contractor Evaluation tab to evaluate your contractor.

## Contractor Evaluation
Contractor Performance Evaluation
Document Number: | [6 empty] | Contractor Name:
Division: |  |  |  |  | RPAM
Description (as per document):
Contract Start Date: | [7 empty] | Substantial Performance Date:
Evaluation Type: |  |  |  |  | Final
Item | Weight | Score | Percentage | Criteria |  |  |  |  | Evaluation | Comments
| 6 | 0 | 0 | Project Commencement (6%)
1 | 4 | 0 |  | Did the project/construction commence by the contractually obligated date or Region agreed/revised start date?
2 | 2 | 0 |  | Was an acceptable baseline schedule (inclusive of key tasks, activities, subs, and schedule of values/cash flow projections when requested, etc.) provided at the pre-construction meeting or within the agreed-upon timeframe?
| 14 | 0 | 0 | Project Management (14%)
3 | 4 | 0 |  | Did the Contractor maintain comprehensive and realistic schedule updates and provide updates as required? (e.g. phasing work, time extension allowances, etc.)
4 | 4 | 0 |  | Did the Contractor meet the project milestones by the contractually obligated date or any other agreed-upon dates?
5 | 3 | 0 |  | Did the Contractor provide timely and adequate notification to Agency as-required, considering site requirements specific to facility types (e.g. Long-Term Care Facility/ Residential/ Commercial Properties)?
6 | 3 | 0 |  | Did the Contractor submit the specified submittals on-time and in the proper formats (e.g. shop drawings, substitutions, test results, commissioning plan, etc.)?
| 26 | 0 | 0 | Workmanship (26%)
7 | 2 | 0 |  | Did the Contractor comply with all permit requirements and agreements?
8 | 2 | 0 |  | Did the Contractor install and maintain all environmental measures as per Contract and Permit requirements and mitigate all identified environmental site issues in a timely manner? (e.g. infection control)
9 | 2 | 0 |  | Did the Contractor cause any damage to existing facilities, properties (City, Region or private), sites, etc.?
10 | 2 | 0 |  | Did the Contractor comply with the allowable working hours as specified in the Contract or as approved by the Agency?
11 | 3 | 0 |  | Was the equipment utilized by the Contractor for the completion of the work as specified within the contract/agreed-upon by Agency?
12 | 3 | 0 |  | Did the materials (including mock-ups and equipment to be installed) supplied by the Contractor meet the Contract specifications?
13 | 3 | 0 |  | Did the Contractor stage the work in an appropriate manner to achieve the Contract requirements?
14 | 3 | 0 |  | Did the Contractor supply appropriate staff for the required work and/or did the staff have the appropriate skills, training and licenses required?
15 | 3 | 0 |  | Did the Contractor resolve deficiencies identified during construction in a timely manner and to the satisfaction of the Agency?
16 | 3 | 0 |  | Did the Contractor pass the minimum testing requirements (e.g. pressure testing, leakage test, FAT, SAT, Compaction, Material Testing, etc.)?
| 12 | 0 | 0 | Safety (12%)
17 | 2 | 0 |  | Did the Contractor keep the site (including emergency access routes and control public access) reasonably clean/clear, safe and organized throughout the duration of the project?
18 | 1 | 0 |  | Did the Contractor submit an acceptable Safety Plan in a timely manner prior to commencement and keep a copy on-site for the Contract duration?
19 | 1 | 0 |  | Did the Contractor keep required notices in an accessible location on site: OH&SA, Construction Regs, Nearest MOL office, First Aid Regs, WSIB Poster (Form 82), H&S Policy, MSDS, Emergency Procedures, and NOP and Form 1000 for each sub-contractor, etc.?
20 | 1 | 0 |  | Did the Contractor obtain up-to-date locates for all utilities and were they kept up-to-date throughout project duration, while adhering to all locate conditions?
21 | 1 | 0 |  | Did all Contractor and sub-contractor staff wear the required PPE on site?
22 | 2 | 0 |  | Did the Contractor take immediate Action to rectify safety issues?
23 | 2 | 0 |  | As required, did the Contractor deal with incidents/accidents to the General Public and report to the Region and other Authorities Having Jurisdiction in a timely manner?
24 | 2 | 0 |  | Did the Contractor comply with any stop work orders issued by the Region, MOL, TSSA, other Agencies?
| 18 | 0 | 0 | Contract Management and Supervision (18%)
25 | 3 | 0 |  | Did the Contractor submit unjustifiable change order requests?
26 | 3 | 0 |  | Did the Contractor submit reasonable and competitive quotations for extra work (including change directives), in a timely manner?
27 | 2 | 0 |  | Did the Contractor follow the contractual claims procedure (including the resolution of all claims) in a timely manner?
28 | 2 | 0 |  | Did the Contractor comply with any written notices by the Agency in a timely manner (e.g. site instructions, change directives, etc.)?
29 | 2 | 0 |  | Did the Contractor submit payment requests (progress invoices) accurately which were inclusive of WSIB and Statutory declaration for each invoice submitted?
30 | 3 | 0 |  | Did the Contractor have the appropriate and qualified authority on site to make decisions and provide continuous on-site supervision to workers?
31 | 3 | 0 |  | Did the Contractor effectively coordinate with Sub-Contractors, Suppliers, other Contractors, and Consultants as applicable and in a timely manner? (e.g. regular interference, drawings, performance concerns, etc.)
| 6 | 0 | 0 | Client and Public Relations (6%)
32 | 2 | 0 |  | Did the Contractor respond appropriately to service delivery issues (complaints, inquiries, third party claims, liens, etc.)?
33 | 4 | 0 |  | Was the Contractor fair and did they conduct themselves with common courtesy and appropriate business manner when dealing with the Public, Agency staff/ representatives, and own employees (e.g. properly identifying themselves to the Public and Agency staff as required)?
| 18 | 0 | 0 | Project Completion (18%)
34 | 3 | 0 |  | Did the Contractor provide complete start-up/commissioning services of all equipment/systems (e.g. BAS, access controls, networking, M&E, etc.) and resolve all issues, in a timely manner?
35 | 2 | 0 |  | Did the Contractor provide complete training of Maintenance personnel in use of building systems, in accordance with the contract documents?
36 | 2 | 0 |  | Did the Contractor meet the Substantial Performance by the contractually obligated date(s) or revised agreed-upon date(s)?
37 | 2 | 0 |  | Did the Contractor meet the Occupancy and Permit Close-Out by the contractually obligated date(s) or revised agreed-upon date(s)?
38 | 3 | 0 |  | Did the Contractor make good all deficiencies and issues identified to the full satisfaction of the Agency?
39 | 3 | 0 |  | Did the Contractor submit on schedule complete Operations and Maintenance Manuals as well as accurate and/or complete record documents and drawings?
40 | 3 | 0 |  | Did the Contractor meet the requirements of Substantial Performance (e.g. warranties, operational manuals, as-built drawings, etc.) by the contractually obligated date or revised agreed-upon date?
Maximum Point Available |  |  |  |  | 100 | Comments:
Points Earned |  |  |  |  | 0
TOTAL PERCENTAGE |  |  |  |  | 0%
Contractor Rating
Approval Required
Region's Project Manager Name: | [8 empty] | Date:
Region's Project Manager Signature:
Approval Name: | [8 empty] | Date:
Approval Signature:
Please send all signed final evaluations to vendorperformance@peelregion.ca
V-20180305

## Additional Comments
This sheet provides a space for project managers to log additional comments, it is recommended to use when there are performance issues.
Item | Criteria | Additional Comments
1 | Did the project/construction commence by the contractually obligated date or Region agreed/revised start date?
2 | Was an acceptable baseline schedule (inclusive of key tasks, activities, subs, and schedule of values/cash flow projections when requested, etc.) provided at the pre-construction meeting or within the agreed upon timeframe?
Project Management
3 | Did the Contractor maintain comprehensive and realistic schedule updates and provide updates as required? (e.g. phasing work, time extension allowances, etc.)
4 | Did the Contractor meet the project milestones by the contractually obligated date or any other agreed-upon dates?
5 | Did the Contractor provide timely and adequate notification to Agency as-required, considering specific site requirements (e.g. Long-Term Care Facility/Residential/Commercial Properties)?
6 | Did the Contractor submit the specified submittals on-time and in the proper formats (e.g. show drawings, substitutions, test results, commissioning plan, etc.)?
Workmanship
7 | Did the Contractor comply with all permit requirements and agreements?
8 | Did the Contractor install and maintain all environmental measures as per Contract and Permit requirements and mitigate all identified environmental site issues in a timely manner? (e.g. infection control)
9 | Did the Contractor cause any damage to existing facilities, properties (City, Region or private), sites, etc?
10 | Did the Contractor comply with the allowable working hours as specified in the Contract or as approved by the Agency?
11 | Was the equipment utilized by the Contractor for the completion of the work as specified within the contract/agreed-upon by Agency?
12 | Did the materials (including mock-ups and equipment to be installed) supplied by the Contractor meet the Contract specifications?
13 | Did the Contractor stage the work in an appropriate manner to achieve the Contract requirements?
14 | Did the Contractor supply appropriate staff for the required work and/or did the staff have the appropriate skills, training and licenses required?
15 | Did the Contractor resolve deficiencies identified during construction in a timely manner and to the satisfaction of the Agency?
16 | Did the Contractor pass the minimum testing requirements (e.g. pressure testing, leakage test, FAT, SAT, Compaction, Material Testing, etc.)?
Safety
17 | Did the Contractor keep the site (including emergency access routes and control public access) reasonably clean/clear, safe and organized throughout the duration of the project?
18 | Did the Contractor submit an acceptable Safety Plan in a timely manner prior to commencement and keep a copy on-site for the Contract duration?
19 | Did the Contractor keep required notices in an accessible location on site: OH&SA, Construction Regs, Nearest MOL office, First Aid Regs, WSIB Poster (Form 82), H&S Policy, MSDS, Emergency Procedures, and NOP and Form 1000 for each sub-contractor, etc.?
20 | Did the Contractor obtain up-to-date locates for all utilities and were they kept up-to-date throughout project duration, while adhering to all locate conditions?
21 | Did all Contractor and sub-contractor staff wear the required PPE on site?
22 | Did the Contractor take immediate Action to rectify safety issues?
23 | As required, did the Contractor deal with incidents/accidents to the General Public and report to the Region and other Authorities Having Jurisdiction in a timely manner?
24 | Did the Contractor comply with any stop work orders issued by the Region, MOL, TSSA, other Agencies?
Contract Management and Supervision
25 | Did the Contractor submit unjustifiable change order requests?
26 | Did the Contractor submit reasonable and competitive quotations for extra work (including change directives), in a timely manner?
27 | Did the Contractor follow the contractual claims procedure (including the resolution of all claims) in a timely manner?
28 | Did the Contractor comply with any written notices by the Agency in a timely manner (e.g. site instructions, change directives, etc.)?
29 | Did the Contractor submit payment requests (progress invoices) accurately which were inclusive of WSIB and Statutory declaration for each invoice submitted?
30 | Did the Contractor have the appropriate and qualified authority on site to make decisions and provide continuous on-site supervison to workers?
31 | Did the Contractor effectively coordinate with Sub-Contractors, Suppliers, other Contractors, and Consultants as applicable and in a timely manner? (e.g. regular interference, drawings, performance concerns, etc.)
Client and Public Relations
32 | Did the Contractor respond appropriately to service delivery issues (complaints, inquiries, third party claims, liens, etc.)?
33 | Was the Contractor fair and did they conduct themselves with common courtesy and appropriate business manner when dealing with the Public, Agency staff/ representatives, and own employees (e.g. properly identifing themselves to the Public and Agency staff as required)?
Project Completion
34 | Did the Contractor provide complete start-up/commissioning services of all equipment/systems (e.g. BAS, access controls, networking, M&E, etc.), and resolve all issues, in a timely manner?
35 | Did the Contractor provide complete training of Maintenance personnel in use of building systems, in accordance with the contract documents?
36 | Did the Contractor meet the Substantial Performance by the contractually obligated date(s) or revised agreed-upon date(s)?
37 | Did the Contractor meet the Occupancy and Permit Close-Out by the contractually obligated date(s) or revised agreed-upon date(s)?
38 | Did the Contractor make good all deficiencies and issues identified to the full satisfaction of the Agency?
39 | Did the Contractor submit on schedule complete Operations and Maintenance Manuals as well as accurate and/or complete record documents and drawings?
40 | Did the Contractor meet the requirements of Final Completion by the contractually obligated date or revised agreed-upon date?

## Automation Weight Options (hidden)
Weight Options
| Interim | Not Applicable | Not Applicable | Not Applicable
| Final | 4 | 3 | 2
| Yes | 3 | Yes | 2 | Yes | 4 | Yes | 1
| No | Not Applicable | No | Not Applicable | No | Not Applicable | No | Not Applicable

## AutomationCriteria Menu Options (hidden)
Specific |  |  | Options | Weight | Yes, No Option |  |  | Options | Weight
Project Commencement | 2 | Was an acceptable baseline schedule (inclusive of key tasks, activities, subs and schedule of values/cash flow projections when requested, etc.) provided at the pre-construction meeting or within the agreed upon timeframe? | Yes or Minor Revisions | 100 | Project Commencement | 4 | Did the project/construction commence by the contractually obligated date or Region agreed start date? | Yes | 100
Safety | 1 | Did the Contractor submit an acceptable Safety Plan in a timely manner prior to commencement and keep a copy on-site for the Contract duration? | Received but required re-submission(s) | 50 | Safety | 1 | Did the Contractor keep required notices in an accessible location on site: OH&SA, Construction Regs, Nearest MOL office, First Aid Regs, WSIB Poster (Form 82), H&S Policy, MSDS, Emergency Procedures, and NOP and Form 1000 for each sub-contractor, etc.? | No | 0
|  |  | No | 0 | Safety | 2 | As required, did the Contractor deal with incidents/accidents to the General Public and report to the Region and other Authorities Having Jurisdiction in a timely manner?
[5 empty] | Safety | 2 | Did the Contractor comply with any stop work orders issued by the Region, MOL, TSSA, other Agencies?
Specific |  |  | Options | Weight | Project Completion | 3 | Did the Contractor provide complete start-up/commissioning services of all equipment/systems (e.g. BAS, access controls, networking, M&E, etc.) and resolve all issues, in a timely manner?
Workmanship | 2 | Did the Contractor cause any damage to existing facilities, properties (City, Region or Private), sites, etc.? | No Damage Occurred | 100 | Project Completion | 3 | Did the Contractor provide complete training of Maintenance personnel in use of building systems, in accordance with the contract documents?
|  |  | Incurred Minor Damage | 50 | Project Completion | 3 | Did the Contractor meet the Substantial Performance by the contractually obligated date(s) or revised agreed-upon date(s)?
|  |  | Incurred Extensive Damage | 0 | Project Completion | 3 | Did the Contractor meet the Occupancy and Permit Close-Out by the contractually obligated date(s) or revised agreed-upon date(s)?
[5 empty] | Project Completion | 3 | Did the Contractor make good all deficiencies and issues identified to the full satisfaction of the Agency?
Specific |  |  | Options | Weight | Project Completion | 3 | Did the Contractor submit on schedule complete Operations and Maintenance Manuals as well as accurate and/or complete record documents and drawings?
Workmanship | 3 | Did the materials (including mock-ups and equipment to be installed) supplied by the Contractor meet the Contract specifications? | Yes, Met All Specifications | 100 | Project Completion | 2 | Did the Contractor meet the requirements of Substantial Performance (e.g. warranties, operational manuals, as-built drawings, etc.) by the contractually obligated date or revised agreed-upon date?
|  |  | Incurred a Few Rejections of Materials | 50
|  |  | Incurred Many Rejections of Materials | 0 | Always, Usually, Sometimes, Rarely/Near Option |  |  | Options | Weight
[5 empty] | Project Management | 4 | Did the Contractor maintain comprehensive and realistic schedule updates and provide updates as required? (e.g. phasing work, time extension allowances) | Always | 100
Reverse Always, Sometimes, Never Rarely |  |  | Options | Weight | Project Management | 3 | Did the Contractor provide timely and adequate notification to the Agency as-required considering specific site requirements specific to facility types (e.g. Long-Term Care Facility/Residential/Commercial Properties)? | Usually | 67
Contract Management & Supervision | 2 | Did the Contractor submit unjustifiable change order requests? | Rarely/Never | 100 | Project Management | 3 | Did the Contractor submit the specified submittals on-time and in the proper formats (e.g. shop drawings, substitutions, test results, commissioning plan, etc.)? | Sometimes | 33
|  |  | Sometimes | 67 | Workmanship | 2 | Did the Contractor comply with all permit requirements and agreements? | Rarely/Never | 0
|  |  | Usually | 33 | Workmanship | 2 | Did the Contractor install and maintain all environmental measures as per Contract and Permit requirements and mitigate all identified environmental site issues in a timely manner? (e.g. infection control)
|  |  | Always | 0 | Workmanship | 2 | Did the Contractor comply with the allowable working hours as specified in the Contract or as approved by the Agency?
[5 empty] | Workmanship | 2 | Was the equipment utilized by the Contractor for the completion of the work as specified within the contract/agreed-upon by Agency?
Yes, Met Most (No Major Impact), No (Major Impact) Option |  |  | Options | Weight | Workmanship | 2 | Did the Contractor stage the work in an appropriate manner to achieve the Contract requirements?
Project Management | 3 | Did the Contractor meet the project milestones by the contractually obligated date or any other agreed-upon dates? | Yes | 100 | Workmanship | 3 | Did the Contractor supply appropriate staff for the required work and/or did the staff have the appropriate skills, training and licenses required?
|  |  | No (No Major Impact) | 50 | Workmanship | 3 | Did the Contractor resolve deficiencies identified during construction in a timely manner and to the satisfaction of the Agency?
|  |  | No (Major Impact) | 0 | Workmanship | 3 | Did the Contractor pass the minimum testing requirements (e.g. pressure testing, leakage test, FAT, SAT, Compaction, Material Testing, etc.)?
[5 empty] | Safety | 2 | Did the Contractor keep the site (including emergency access routes and control public access) reasonably clean/clear, safe and organized throughout the duration of the project?
Yes, No Option |  |  | Options | Weight | Safety | 1 | Did the Contractor obtain up-to-date locates for all utilities and were they kept up-to-date throughout project duration, while adhering to all locate conditions?
Client and Public Relations | 3 | Was the Contractor fair and did they conduct themselves with common courtesy and appropriate business manner when dealing with Public, Agency Staff / representatives, and own employees (e.g. properly identifying themselves to the Public and Agency staff as required)? | Yes | 100 | Safety | 1 | Did all Contractor and Sub-Contractor staff wear the required PPE on site?
|  |  | Usually (Minor Issues) | 50 | Safety | 2 | Did the Contractor take immediate Action to rectify safety issues?
|  |  | No (Major Issue) | 0 | Contract Management and Supervision | 2 | Did the Contractor submit reasonable and competitive quotations for extra work (including change directives), in a timely manner?
[5 empty] | Contract Management and Supervision | 2 | Did the Contractor follow the contractual claims procedure (including the resolution of all claims) in a timely manner?
[5 empty] | Contract Management and Supervision | 3 | Did the Contractor comply with any written notices by the Agency in a timely manner (e.g. site instructions, change directives, etc.)?
[5 empty] | Contract Management and Supervision | 3 | Did the Contractor submit payment requests (progress invoices) accurately which were inclusive of WSIB and Statutory declaration for each invoice submitted?
[5 empty] | Contract Management and Supervision | 2 | Did the Contractor have the appropriate and qualified authority on site to make decisions and provide continuous on-site supervision to workers?
[5 empty] | Contract Management and Supervision | 2 | Did the Contractor effectively coordinate with Sub-Contractors, Suppliers, other Contractors, and Consultants as applicable and in a timely manner? (e.g. regular interference, drawings, performance concerns, etc.)
[5 empty] | Client and Public Relations | 3 | Did the Contractor respond appropriately to service delivery issues (complaints, inquiries, third party claims, liens, etc.)?

## Contractor Evaluation Guide
Contractor Performance Evaluation Guide
Document Number: | [6 empty] | Contractor Name:
Description (as per document):
Contract Start Date: | [7 empty] | Substantial Performance Date:
Evaluation Type: |  |  |  |  | Final
Item | Weight | Score |  | Criteria |  |  |  |  | Evaluation Guide
| 6 | 0 | Percentage | Project Commencement
1 | 4 | 0 |  | Did the project/construction commence by the contractually obligated date or Region agreed/revised start date? |  |  |  |  | Yes/No
2 | 2 | 0 |  | Was an acceptable baseline schedule (inclusive of key tasks, activities, subs, and schedule of values/cash flow projections when requested, etc.) provided at the pre-construction meeting or within the agreed-upon timeframe? |  |  |  |  | Yes or Minor Revisions/ Received but Required Re-submissions/ No
| 14 | 0 |  | Project Management
3 | 4 | 0 |  | Did the Contractor maintain comprehensive and realistic schedule updates and provide updates as required? (e.g. phasing work, time extension allowances, etc.) |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
4 | 4 | 0 |  | Did the Contractor meet the project milestones by the contractually obligated date or any other agreed-upon dates? |  |  |  |  | Yes/ No (No Major Impact)/ No (Major Impact)
5 | 3 | 0 |  | Did the Contractor provide timely and adequate notification to Agency as-required, considering site requirements specific to facility types (e.g. Long-Term Care Facility/ Residential/ Commercial Properties)? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
6 | 3 | 0 |  | Did the Contractor submit the specified submittals on-time and in the proper formats (e.g. shop drawings, substitutions, test results, commissioning plan, etc.)? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
| 26 | 0 |  | Workmanship
7 | 2 | 0 |  | Did the Contractor comply with all permit requirements and agreements? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
8 | 2 | 0 |  | Did the Contractor install and maintain all environmental measures as per Contract and Permit requirements and mitigate all identified environmental site issues in a timely manner? (e.g. infection control) |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
9 | 2 | 0 |  | Did the Contractor cause any damage to existing facilities, properties (City, Region or private), sites, etc.? |  |  |  |  | No Damage Occurred/ Incurred Minor Damage/ Incurred Extensive Damage
10 | 2 | 0 |  | Did the Contractor comply with the allowable working hours as specified in the Contract or as approved by the Agency? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
11 | 3 | 0 |  | Was the equipment utilized by the Contractor for the completion of the work as specified within the contract/agreed-upon by Agency? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
12 | 3 | 0 |  | Did the materials (including mock-ups and equipment to be installed) supplied by the Contractor meet the Contract specifications? |  |  |  |  | Yes, Met all Specifications/ Incurred a Few Rejections of Materials/ Incurred Many Rejections of Materials
13 | 3 | 0 |  | Did the Contractor stage the work in an appropriate manner to achieve the Contract requirements? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
14 | 3 | 0 |  | Did the Contractor supply appropriate staff for the required work and/or did the staff have the appropriate skills, training and licenses required? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
15 | 3 | 0 |  | Did the Contractor resolve deficiencies identified during construction in a timely manner and to the satisfaction of the Agency? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
16 | 3 | 0 |  | Did the Contractor pass the minimum testing requirements (e.g. pressure testing, leakage test, FAT, SAT, Compaction, Material Testing, etc.)? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
| 12 | 0 |  | Safety
17 | 2 | 0 |  | Did the Contractor keep the site (including emergency access routes and control public access) reasonably clean/clear, safe and organized throughout the duration of the project? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
18 | 1 | 0 |  | Did the Contractor submit an acceptable Safety Plan in a timely manner prior to commencement and keep a copy on-site for the Contract duration? |  |  |  |  | Yes or Minor Revisions/ Received but Required Re-submissions/ No
19 | 1 | 0 |  | Did the Contractor keep required notices in an accessible location on site: OH&SA, Construction Regs, Nearest MOL office, First Aid Regs, WSIB Poster (Form 82), H&S Policy, MSDS, Emergency Procedures, and NOP and Form 1000 for each sub-contractor, etc.? |  |  |  |  | Yes/No
20 | 1 | 0 |  | Did the Contractor obtain up-to-date locates for all utilities and were they kept up-to-date throughout project duration, while adhering to all locate conditions? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
21 | 1 | 0 |  | Did all Contractor and sub-contractor staff wear the required PPE on site? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
22 | 2 | 0 |  | Did the Contractor take immediate Action to rectify safety issues? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
23 | 2 | 0 |  | As required, did the Contractor deal with incidents/accidents to the General Public and report to the Region and other Authorities Having Jurisdiction in a timely manner? |  |  |  |  | Yes/No
24 | 2 | 0 |  | Did the Contractor comply with any stop work orders issued by the Region, MOL, TSSA, other Agencies? |  |  |  |  | Yes/No
| 18 | 0 |  | Contract Management and Supervision
25 | 3 | 0 |  | Did the Contractor submit unjustifiable change order requests? |  |  |  |  | Rarely or Never/Sometimes/Usually/Always
26 | 3 | 0 |  | Did the Contractor submit reasonable and competitive quotations for extra work (including change directives), in a timely manner? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
27 | 2 | 0 |  | Did the Contractor follow the contractual claims procedure (including the resolution of all claims) in a timely manner? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
28 | 2 | 0 |  | Did the Contractor comply with any written notices by the Agency in a timely manner (e.g. site instructions, change directives, etc.)? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
29 | 2 | 0 |  | Did the Contractor submit payment requests (progress invoices) accurately which were inclusive of WSIB and Statutory declaration for each invoice submitted? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
30 | 3 | 0 |  | Did the Contractor have the appropriate and qualified authority on site to make decisions and provide continuous on-site supervision to workers? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
31 | 3 | 0 |  | Did the Contractor effectively coordinate with Sub-Contractors, Suppliers, other Contractors, and Consultants as applicable and in a timely manner? (e.g. regular interference, drawings, performance concerns, etc.) |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
| 6 | 0 |  | Client and Public Relations
32 | 2 | 0 |  | Did the Contractor respond appropriately to service delivery issues (complaints, inquiries, third party claims, liens, etc.)? |  |  |  |  | Always/Usually/Sometimes/Rarely or Never
33 | 4 | 0 |  | Was the Contractor fair and did they conduct themselves with common courtesy and appropriate business manner when dealing with the Public, Agency staff/ representatives, and own employees (e.g. properly identifying themselves to the Public and Agency staff as required)? |  |  |  |  | Yes/ Usually (Minor Issues)/ No (Major Issue)
| 18 | 0 |  | Project Completion
34 | 3 | 0 |  | Did the Contractor provide complete start-up/commissioning services of all equipment/systems (e.g. BAS, access controls, networking, M&E, etc.) and resolve all issues, in a timely manner? |  |  |  |  | Yes/No
35 | 2 | 0 |  | Did the Contractor provide complete training of Maintenance personnel in use of building systems, in accordance with the contract documents? |  |  |  |  | Yes/No
36 | 2 | 0 | 0 | Did the Contractor meet the Substantial Performance by the contractually obligated date(s) or revised agreed-upon date(s)? |  |  |  |  | Yes/No
37 | 2 | 0 |  | Did the Contractor meet the Occupancy and Permit Close-Out by the contractually obligated date(s) or revised agreed-upon date(s)? |  |  |  |  | Yes/No
38 | 3 | 0 |  | Did the Contractor make good all deficiencies and issues identified to the full satisfaction of the Agency? |  |  |  |  | Yes/No
39 | 3 | 0 |  | Did the Contractor submit on schedule complete Operations and Maintenance Manuals as well as accurate and/or complete record documents and drawings? |  |  |  |  | Yes/No
40 | 3 | 0 |  | Did the Contractor meet the requirements of Substantial Performance (e.g. warranties, operational manuals, as-built drawings, etc.) by the contractually obligated date or revised agreed-upon date? |  |  |  |  | Yes/No
Maximum Point Available |  |  |  |  | 100 | Comments:
Points Earned |  |  |  |  | 0
TOTAL PERCENTAGE |  |  |  |  | 0%
Contractor Rating
Approval Required
Region's Project Manager Name: | [8 empty] | Date:
Region's Project Manager Signature:
Approval Name: | [8 empty] | Date:
Approval Signature: