## Pre-Evaluation Questionnaire
Contractor Performance Evaluation Questionnaire
Please complete this set of questions prior to starting your evaluation to ensure the evaluation template is customized to suit your particular project and / or the stage you are at in your project.
Is this the Final Evaluation or an Interim Evaluation? | Final
Have there been any Change Orders? | Yes
Have any submittals (other than the baseline schedule) been required from the Contractor yet? | Yes
Have there been any deficiencies? | Yes
Has testing commenced and/or completed? | Yes
Were there any incidents/accidents involving the General Public? | Yes
Has the Contractor received any written notices? | Yes
Have there been any service delivery issues (ie/ complaints, inquiries, claims)? | Yes
Was there a Contractually or Region approved start date the Contractor was to meet? | Yes
Was a Traffic Control Plan Required? | Yes
Were there any Safety Issues? | Yes
Were any stop work orders issued by the Region, MOL, TSSA, other Agencies? | Yes
Were there any environmental requirements as part of the work including but not limited Conservation Authority, PTTW, MNR, MOE, etc? | Yes
Does project close-out require Operations and Maintenance Manuals and / or record documents and drawings to be submitted by the Contractor? | Yes
After completing these questions please move on to the Contractor Evaluation tab to evaluate your contractor.

## Contractor Evaluation
Contractor Performance Evaluation
Document Number: | [6 empty] | Contractor Name:
Division:
Description:
(as per document)
Contract Start Date: | [7 empty] | Substantial Performance Date:
Evaluation Type: |  |  |  |  | Final
Item | Weight | Score |  | Criteria |  |  |  |  | Evaluation Guide | Comments
| 5 | 0 | Percentage | Project Commencement (5%)
1 | 2 | 0 |  | Did the project commence by the contractually obligated date or Region agreed/revised start date?
2 | 3 | 0 |  | Was an acceptable baseline schedule (inclusive of key tasks, activities, subs, etc.) provided at the pre-construction meeting (or within the agreed upon timeframe)?
| 13 | 0 |  | Project Management (13%)
3 | 3 | 0 |  | Did the Contractor maintain comprehensive schedule updates and provide updates as required?
4 | 3 | 0 |  | Did the Contractor meet the project milestones by the contractually obligated date or any other agreed-upon dates?
5 | 4 | 0 |  | Did the Contractor provide timely notification to appropriate stakeholders, as required (e.g. all Peel Operations, residents, etc)?
6 | 3 | 0 |  | Did the Contractor submit the required shop drawings and submittals on-time and in the proper formats (e.g. mix designs, commissioning plan, etc.)?
| 31 | 0 |  | Workmanship (31%)
7 | 3 | 0 |  | Did the Contractor comply with all permit requirements and agreements (e.g. Road Occupancy, MTO Encroachment, etc)?
8 | 3 | 0 |  | Did the Contractor install and maintain all environmental measures as per Contract and Permit requirements (e.g. Conservation Authority, PTTW, MNR, MOE, etc.), and mitigate all identified environmental site issues in a timely manner?
9 | 2 | 0 |  | Did the Contractor cause any damage to existing facilities, properties (City, Region or private), sites, etc?
10 | 2 | 0 |  | Did the Contractor comply with the allowable working hours as specified in the Contract or as approved by the Agency?
11 | 3 | 0 |  | Was the equipment utilized by the Contractor for the completion of the work appropriate for the required work?
12 | 3 | 0 |  | Did the materials (including equipment to be installed) supplied by the Contractor meet the Contract specifications?
13 | 3 | 0 |  | Did the Contractor stage the work in an appropriate manner to achieve the Contract requirements?
14 | 3 | 0 |  | Did the Contractor supply appropriate staff for the required work and / or did the staff have the appropriate skills, training and licenses required?
15 | 3 | 0 |  | Did the Contractor effectively coordinate with other Contractors, Consultants, Sub-Contractors and Suppliers as applicable?
16 | 3 | 0 |  | Did the Contractor resolve deficiencies identified during construction in a timely manner and to the satisfaction of the Agency?
17 | 3 | 0 |  | Did the Contractor pass the minimum testing requirements (e.g. pressure testing, leakage test, FAT, SAT, Compaction, Material Testing, etc.)?
| 21 | 0 |  | Safety (21%)
18 | 3 | 0 |  | Did the Contractor keep the site (and access roads) reasonably clean and organized throughout the duration of the project?
19 | 2 | 0 |  | Did the Contractor consistently follow the submitted Traffic Control Plan (as amended throughout Contract) which was inclusive of OTM Book 7 Temporary Conditions?
20 | 1 | 0 |  | Did the Contractor submit a acceptable Safety Plan in a timely manner prior to commencement and keep a copy on-site for the Contract duration?
21 | 1 | 0 |  | Did the Contractor keep the NOP and Form 1000 for each sub-contractor in an accessible location on site?
22 | 1 | 0 |  | Did the Contractor keep these notices in an accessible location on site; OH&SA, Construction Regs, Nearest MOL office, First Aid Regs, WSIB Poster (Form 82), H&S Policy, MSDS, Emergency Procedures, etc.?
23 | 2 | 0 |  | Did the Contractor obtain up to date locates for all utilities and were they kept up to date throughout project duration, while adhering to all locate conditions?
24 | 2 | 0 |  | Did all Contractor and sub-contractor staff wear the required PPE at all times?
25 | 3 | 0 |  | Did the Contractor take immediate Action to rectify safety issues?
26 | 2 | 0 |  | Did the Contractor maintain, as required, clear emergency Routes and control public access?
27 | 2 | 0 |  | As required, did the Contractor deal with incidents / accidents to the General Public and report to the Region in a timely manner?
28 | 2 | 0 |  | Did the Contractor comply with any stop work orders issued by the Region, MOL, TSSA, other Agencies?
| 16 | 0 |  | Contract Management and Supervision (16%)
29 | 3 | 0 |  | Did the Contractor submit an unjustifiable number of invalid change order requests?
30 | 3 | 0 |  | Did the Contractor submit reasonable and competitive quotations for extra work, in a timely manner?
31 | 2 | 0 |  | Did the Contractor follow the contractual claims procedure?
32 | 3 | 0 |  | Did the Contractor comply with any written notices by the Agency in a timely manner (e.g. site instructions, change directives, etc.)?
33 | 2 | 0 |  | Did the Contractor submit payment requests accurately which were inclusive of WSIB and Statutory declaration for each invoice submitted?
34 | 3 | 0 |  | Did the Contractor have the appropriate authority on site to make decisions and provide continuous on-site supervison to workers?
| 6 | 0 |  | Client and Public Relations (6%)
35 | 3 | 0 |  | Did the Contractor respond appropriately to service delivery issues (complaints, inquiries, third party claims, etc.)?
36 | 3 | 0 |  | Was the Contractor fair and did they conduct themselves with common courtesy and appropriate business manner when dealing with the Public, Agency staff / representatives, and own employees (including; properly identifing themselves to the Public and Agency staff as required)?
| 8 | 0 |  | Project Completion (8%)
37 | 4 | 0 |  | Did the Contractor submit on schedule complete Operations and Maintenance Manuals as well as accurate and / or complete record documents and drawings?
38 | 4 | 0 |  | Did the Contractor meet the Substantial Performance by the contractually obligated date or revised agreed-upon date?
Maximum Point Available |  |  |  |  | 100 | Comments:
Points Earned |  |  |  |  | 0
TOTAL PERCENTAGE |  |  |  |  | 0%
Contractor Rating
Approval Required
Region's Project Manager Name: | [8 empty] | Date:
Region's Project Manager Signature:
Approval Name: | [8 empty] | Date:
Approval Signature:
Please send all signed final evaluations to vendorperformance@peelregion.ca
V-20180305

## Additional Comments
This sheet provides a space for project managers to log additional comments, it is recommended to use when there are performance issues.
Item | Critiera | Additional Comments
1 | Did the project commence by the contractually obligated date or Region agreed/revised start date?
2 | Was an acceptable baseline schedule (inclusive of key tasks, activities, subs, etc.) provided at the pre-construction meeting (or within the agreed upon timeframe)?
Project Management
3 | Did the Contractor maintain comprehensive schedule updates and provide updates as required?
4 | Did the Contractor meet the project milestones by the contractually obligated date or any other agreed-upon dates?
5 | Did the Contractor provide timely notification to appropriate stakeholders, as required (e.g. all Peel Operations, residents, etc)?
6 | Did the Contractor submit the required shop drawings and submittals on-time and in the proper formats (e.g. mix designs, commissioning plan, etc.)?
Workmanship
7 | Did the Contractor comply with all permit requirements and agreements (eg. Road Occupancy, MTO Encroachment, etc)?
8 | Did the Contractor install and maintain all environmental measures as per Contract and Permit requirements (e.g. Conservation Authority, PTTW, MNR, MOE, etc.), and mitigate all identified environmental site issues in a timely manner?
9 | Did the Contractor cause any damage to existing facilities, properties (City, Region or private), sites, etc?
10 | Did the Contractor comply with the allowable working hours as specified in the Contract or as approved by the Agency?
11 | Was the equipment utilized by the Contractor for the completion of the work appropriate for the required work?
12 | Did the materials (including equipment to be installed) supplied by the Contractor meet the Contract specifications?
13 | Did the Contractor stage the work in an appropriate manner to achieve the Contract requirements?
14 | Did the Contractor supply appropriate staff for the required work and / or did the staff have the appropriate skills, training and licenses required?
15 | Did the Contractor effectively coordinate with other Contractors, Consultants, Sub-Contractors and Suppliers as applicable?
16 | Did the Contractor resolve deficiencies identified during construction in a timely manner and to the satisfaction of the Agency?
17 | Did the Contractor pass the minimum testing requirements (e.g. pressure testing, leakage test, FAT, SAT, Compaction, Material Testing, etc.)?
Safety
18 | Did the Contractor keep the site (and access roads) reasonably clean and organized throughout the duration of the project?
19 | Did the Contractor consistently follow the submitted Traffic Control Plan (as amended throughout Contract) which was inclusive of OTM Book 7 Temporary Conditions?
20 | Did the Contractor submit a acceptable Safety Plan in a timely manner prior to commencement and keep a copy on-site for the Contract duration?
21 | Did the Contractor keep the NOP and Form 1000 for each sub-contractor in an accessible location on site?
22 | Did the Contractor keep these notices in an accessible location on site; OH&SA, Construction Regs, Nearest MOL office, First Aid Regs, WSIB Poster (Form 82), H&S Policy, MSDS, Emergency Procedures, etc.?
23 | Did the Contractor obtain up to date locates for all utilities and were they kept up to date throughout project duration, while adhering to all locate conditions?
24 | Did all Contractor and sub-contractor staff wear the required PPE at all times?
25 | Did the Contractor take immediate Action to rectify safety issues?
26 | Did the Contractor maintain, as required, clear emergency Routes and control public access?
27 | As required, did the Contractor deal with incidents / accidents to the General Public and report to the Region in a timely manner?
28 | Did the Contractor comply with any stop work orders issued by the Region, MOL, TSSA, other Agencies?
Contract Management and Supervision
29 | Did the Contractor submit an unjustifiable number of invalid change order requests?
30 | Did the Contractor submit reasonable and competitive quotations for extra work, in a timely manner?
31 | Did the Contractor follow the contractual claims procedure?
32 | Did the Contractor comply with written notices by the Agency in a timely manner (e.g. site instructions, change directives, etc.)?
33 | Did the Contractor submit payment requests accurately which were inclusive of WSIB and Statutory declaration for each invoice submitted?
34 | Did the Contractor have the appropriate authority on site to make decisions and provide continuous on-site supervison to workers?
Client and Public Relations
35 | Did the Contractor respond appropriately to service delivery issues (complaints, inquiries, third party claims, etc.)?
36 | Was the Contractor fair and did they conduct themselves with common courtesy and appropriate business manner when dealing with the Public, Agency staff / representatives, and own employees (including; properly identifing themselves to the Public and Agency staff as required)?
Project Completion
37 | Did the Contractor submit on schedule complete Operations and Maintenance Manuals as well as accurate and / or complete record documents and drawings?
38 | Did the Contractor meet the Substantial Performance by the contractually obligated date or revised agreed-upon date?

## Automation Weight Options (hidden)
Weight Options
| Interim | Not Applicable
| Final | 4
| Yes | 3 | Yes | 2 | Yes | 4
| No | Not Applicable | No | Not Applicable | No | Not Applicable

## AutomationCriteria Menu Options (hidden)
Specific |  |  | Options | Weight | Yes, No Option |  |  | Options | Weight
Project Commencement | 3 | Was an acceptable baseline schedule (incusive of key tasks, activities, subs, etc.) provided at the pre-construction meeting (or within the agreed upon timeframe)? | Yes or Minor Revisions | 100 | Project Commencement | 2 | Did the project commence by the contractually obligated date or Region-agreed start date? | Yes | 100
Safety | 1 | Did the Contractor submit a acceptable Safety Plan in a timely manner prior to commencement and keep a copy on site for the Contract duration? | Received but required re-submission(s) | 50 | Safety | 1 | Did the Contractor keep the NOP and Form 1000 for each sub-contractor in an accessible location on site? | No | 0
|  |  | No | 0 | Safety | 1 | Did the Contractor keep these notices in an accessible location on site; OH&SA, Construction Regs, Nearest MOL office, First Aid Regs, WSIB Poster (Form 82), H&S Policy, MSDS, Emergency Procedures, etc.?
[5 empty] | Safety | 2 | As required, did the Contractor deal with incidents / accidents to the General Public and report to the Region in a timely manner?
Specific |  |  | Options | Weight | Safety | 2 | Did the Contractor comply with any stop work orders issued by the Region, MOL, TSSA, other Agencies?
Workmanship | 2 | Did the Contractor cause any damage to existing facilities, properties (City, Region or Private), sites, etc? | No Damage Occurred | 100 | Project Completion | 4 | Did the Contractor meet the Substantial Completion by the contractually obligated date or revised agreed-upon date?
|  |  | Incurred Minor Damage | 50
|  |  | Incurred Extensive Damage | 0 | Always, Usually, Sometimes, Rarely/Near Option |  |  | Options | Weight
[5 empty] | Project Management | 3 | Did the Contractor maintain comprehensive schedule updates and provide updates as required? | Always | 100
Specific |  |  | Options | Weight | Project Management | 4 | Did the Contractor provide timely notification to appropriate stakeholders, as required? (e.g. all Peel operations, residents, etc) | Usually | 67
Workmanship | 3 | Did the materials (including equipment to be installed) supplied by the Contractor meet the Contract specifications? | Yes, Met All Specifications | 100 | Project Management | 3 | Did the Contractor submit the required shop drawings and submittals on-time and in the proper formats (e.g. mix designs, commissioning plan, etc.)? | Sometimes | 33
|  |  | Incurred a Few Rejections of Materials | 50 | Workmanship | 3 | Did the Contractor comply with all permit requirements and agreements (eg. Conservation Authority, PTTW, Road Occupancy, MTO Encroachment, etc)? | Rarely/Never | 0
|  |  | Incurred Many Rejections of Materials | 0 | Workmanship | 2 | Did the Contractor comply with the allowable working hours as specified in the Contract or as approved by the Agency?
[5 empty] | Workmanship | 3 | Was the equipment utilized by the Contractor for the completion of the work appropriate for the required work?
Reverse Always, Sometimes, Never Rarely |  |  | Options | Weight | Workmanship | 3 | Did the Contractor effectively coordinate with other Contractors, Consultants, Sub-Contractors and Suppliers as applicable?
Contract Management & Supervision | 3 | Did the Contractor submit an unjustifiable number of invalid change order requests? | Rarely/Never | 100 | Workmanship | 3 | Did the Contractor stage the work in an appropriate manner to achieve the Contract requirements?
|  |  | Sometimes | 67 | Workmanship | 3 | Did the Contractor supply appropriate staff for the required work and / or did the staff have the appropriate skills, training and licenses required?
|  |  | Usually | 33 | Workmanship | 3 | Did the Contractor install and maintain all environmental measures as per Contract and Permit requirements (eg. Conservation Authority, PTTW, MNR, MOE, etc.), and mitigate all identified environmental site issues in a timely manner?
|  |  | Always | 0 | Workmanship | 3 | Did the Contractor pass the minimum testing requirements (eg. pressure testing, leakage test, FAT, SAT, Compaction, Material Testing, etc.)?
[5 empty] | Workmanship | 3 | Did the Contractor resolve deficiencies identified during construction in a timely manner and to the satisfaction of the Agency?
Yes, Item(s) needed to be re-submitted, No Option |  |  | Options | Weight | Safety | 3 | Did the Contractor keep the site (and access roads) reasonably clean and organized throughout the duration of the project?
Project Completion | 4 | Did the Contractor submit on schedule complete Operations and Maintenance Manuals as well as accurate and / or complete record documents and drawings? | Yes | 100 | Safety | 2 | Did the Contractor obtain up to date locates for all utilities and were they kept up to date throughout project duration, while adhering to all locate conditions?
|  |  | Item(s) needed to be re-submitted | 50 | Safety | 2 | Did all Contractor and Sub-Contractor staff wear the required PPE at all times?
|  |  | No | 0 | Safety | 2 | Did the Contractor consistently follow the submitted Traffic Control Plan (as amended throughout Contract) which was inclusive of OTM Book 7 Temporary Conditions?
[5 empty] | Safety | 3 | Did the Contractor take immediate Action to rectify safety issues?
Yes, Met Most (No Major Impact), No (Major Impact) Option |  |  | Options | Weight | Safety | 2 | Did the Contractor maintain, as required, clear emergency Routes and control public access?
Project Management | 3 | Did the Contractor meet the project milestones by the contractually obligated date or any other agreed-upon dates? | Yes | 100 | Contract Management and Supervision | 3 | Did the Contractor comply with any written notices by the Agency in a timely manner (eg. site instructions, change directives, etc.)?
|  |  | No (No Major Impact) | 50 | Contract Management and Supervision | 3 | Did the Contractor have the appropriate authority on site to make decisions and provided continuous on-site supervison to workers?
|  |  | No (Major Impact) | 0 | Contract Management and Supervision | 2 | Did the Contractor follow the contractual claims procedure?
[5 empty] | Contract Management and Supervision | 3 | Did the Contractor submit reasonable and competitive quotations for extra work, in a timely manner?
Yes, No Option |  |  | Options | Weight | Contract Management and Supervision | 2 | Did the Contractor submit payment requests accurately which were inclusive of WSIB and Statutory declaration for each invoice submitted?
Client and Public Relations | 3 | Was the Contractor fair and did they conduct themselves with common courtesy and appropriate business manner when dealing with Public, Agency Staff / representatives, and own employees (including; properly identifing themselves to the Public and Agnecy staff as required)? | Yes | 100 | Client and Public Relations | 3 | Did the Contractor respond appropriately to service delivery issues (complaints, inquiries, third party claims, etc.)?
|  |  | Usually (Minor Issues) | 50
|  |  | No (Major Issue) | 0