## Sheet1
Electrical Equipment Installation Start Up Checklist
Project Name:
Region Contract No.: |  |  | Contractor:
Date:
Equipment
Process Area
Specification/Drawing Reference
Tag No.
Manufacturer/Supplier
Model
Serial Number
Rating HP/KW |  |  | RPM
Amps |  |  | Supply Voltage
Phase |  |  | Wire
Insulation Design |  |  | Insulation Class
Temperature Raise |  |  | Enclosure Type
Shop Drawing No. |  |  | Date Received
Approvals CSA,NEMA, etc. |  |  | Date Installed
Shop Drawing Status |  |  | Date Inspected/ Verified by Manufacturer
Legend: (A) Inspected and found acceptable (B) Inspected, found defective (C) Not inspected (D) Not Applicable
| INSTALLATION | A | B | C | D
1 | Foundation or Base
2 | Mounting Bolts
3 | Couplings, belts, chains
4 | Shaft Alignment
5 | Gaskets
6 | Motor Megger
7 | Motor Rotation
8 | Supply/Starter Fuse Size
9 | Supply/Starter O/L Size
10 | Interlock Checked
11 | Grounding Installation
12 | Cable or Conduit Installation
Remarks:
| START UP OF EQUIPMENT | A | B | C | D
1 | General Condition
2 | Bearing Temperature
3 | Seals, Packing
4 | Valves, Check valves
5 | Connecting Rods
6 | Couplings
7 | Flights, Scrapers
8 | Safety Hazards
9 | Lubrication
10 | Seal Lubrication
11 | Shafting, Universal
12 | Clutch
13 | Gear Drives
14 | Control – Local Run
15 | Control – Remote Run
16 | Paint Condition
17 | Manufacturer’s Letter of Confirmation of Equipment Proper Installation Received
Remarks:
Inspection Result (Check option that applies) | Passed Installation and Start-up checkout. Equipment certified ready for service |  |  | Failed – Contractor to schedule equipment re-inspection
Contractor’s Signature |  |  | Inspector’s Signature
Date |  |  | Date